## Annual Level for Board (hidden)
Tacoma-Cascade Pipeline (TCP) Project: Annual-Level Work Plan Through 2030
|  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Begin Construction
Projects
Overall TCP |  | 2025: ▪Planning; 2026: ☑Planning ▪Franchise & ROW; 2027: Franchise & ROW
TCP Central Segment |  |  | ▪Planning | ☑Planning | ☑Presdesign | ☑30% Design | ☑Final Design | ▪Begin Constr.
TCP North Segment |  |  | ▪Planning | ☑Planning |  | ☑Predesign | ☑30% Design | ☑60% Design
TCP Other (e.g. BKR) |  | 2025: ▪Planning; 2026: ☑Planning
Facilities Plan |  | 2025: ▪SEPA Review; 2026: ☑Planning
Wheeling |  | 2025: ▪Planning; 2026: ☑Planning; 2027: Legislation (if needed)
South Segment | bar: 2025 to 2030
Lake Tapps Phase 1 | bar: 2025 to 2030
Lake Tapps Phase 2 | bar: 2025 to 2030
New Staff Resources
|  |  | ▪Planning Mgr (Fall 24) |  | ▪Design Section Mgr |  | ▪Constr. Mgr
|  |  | ▪Project Director |  | ▪Program Section Mgr |  | ▪O&M Mgr (25%)
|  |  | ▪Support Engineer |  | ▪Govt Relations / Comms
▪Project Controls
▪Admin & Support
Consulting Resources
Facilities Plan Consultant
Support Services Consultant (owner's rep)
Franchise & ROW Consultant
Central Design Consultant
Central Construction Contract
North Design Consultant
Products & Outcomes
|  |  | Project Funding Plan | Project Baseline | Basis of Design
|  |  | Project Execution Plan | Project Requirements |  |  | 2029 Decision-point on Wheeling
|  |  | Procurement Managment Plan | Risk Managment Plan
|  |  | Stakeholder Management Plan | System Operational Plan
Contract SEPA
|  |  | TSP SEPA |  |  |  | Central SEPA
Note on D43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: this includes real property procurement, consultants and contractors.
Note on E42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This includes system wide requirements

## Biennium Level
Tacoma-Cascade Pipeline (TCP) Project: Biennium-Level Work Plan
|  | 2025 | 2026 | 2027-2028 | 2029-2030 | 2031-2032 | 2033-2034 | 2035-2036 | 2037-2038 | 2039-2040 | 2041-2042 | 2043-2044 | 2045-2046 | 2047-2048 | 2049-2050 | 2051-2052 | 2053-2054 | 2055-2056
[5 empty] | Begin Construction | [5 empty] | Begin using Tacoma Water
Projects
Overall TCP |  | 2025: ▪Planning; 2026: ☑Planning ▪Franchise & ROW; 2027-2028: Franchise & ROW; 2031-2032: Franchise & ROW; 2035-2036: ☑Planning; 2045-2046: ☑Planning; 2055-2056: ☑Planning
Central Segment |  | 2025: ▪Planning; 2026: ☑Planning; 2027-2028: ☑Presdesign ☑30% Design; 2029-2030: ☑Final Design ▪Begin Constr.; 2031-2032: Construction; 2033-2034: ☑Construction Complete; 2035-2036: Schedule float; 2037-2038: Schedule float; 2039-2040: Schedule float
North Segment |  | 2025: ▪Planning; 2026: ☑Planning; 2027-2028: ☑Predesign; 2029-2030: ☑30% Design ☑60% Design; 2031-2032: ☑Final Design; 2033-2034: ▪Begin Constr.; 2035-2036: Construction; 2037-2038: ☑Construction Complete; 2039-2040: Schedule float
Parallel BIP |  | 2025: ▪Planning; 2026: ☑Planning; 2039-2040: ☑Predesign; 2041-2042: ☑30% Design ☑60% Design; 2043-2044: ☑Final Design ▪Begin Constr.; 2045-2046: ☑Construction Complete
Booster Pump Station |  | 2025: ▪Planning; 2026: ☑Planning; 2039-2040: ☑Presdesign ☑30% Design; 2041-2042: ☑Final Design ▪Begin Constr.; 2043-2044: ☑Construction Complete
Storage / Facilities |  | 2025: ▪Planning; 2026: ☑Planning; 2041-2042: ☑Predesign; 2043-2044: ☑30% Design ☑60% Design; 2045-2046: ☑Final Design ▪Begin Constr.; 2047-2048: ☑Construction Complete
Eastside Connections |  | 2025: ▪Planning; 2026: ☑Planning; 2041-2042: ☑Predesign; 2043-2044: ☑30% Design ☑60% Design; 2045-2046: ☑Final Design ▪Begin Constr.; 2047-2048: ☑Construction Complete
BKR Bellevue |  | 2025: ▪Planning; 2026: ☑Planning; 2043-2044: ☑Predesign; 2045-2046: ☑30% Design ☑60% Design; 2047-2048: ☑Final Design ▪Begin Constr.; 2049-2050: ☑Construction Complete
BKR Kirkland/Redmond |  | 2025: ▪Planning; 2026: ☑Planning; 2047-2048: ☑Predesign; 2049-2050: ☑30% Design ☑60% Design; 2051-2052: ☑Final Design ▪Begin Constr.; 2053-2054: ☑Construction Complete
BKR Kirkland/Redmond North |  | 2025: ▪Planning; 2026: ☑Planning; 2049-2050: ☑Predesign; 2051-2052: ☑30% Design ☑60% Design; 2053-2054: ☑Final Design ▪Begin Constr.; 2055-2056: ☑Construction Complete
Wheeling |  | 2025: ▪Planning; 2026: ☑Planning; 2027-2028: Legislation (if needed)
South Segment |  | 2055-2056: ☑Presdesign ☑30% Design
Lake Tapps Phase 1 |  | 2053-2054: ☑Predesign; 2055-2056: ☑30% Design ☑60% Design
Lake Tapps Phase 2 | bar: 2025 to 2029-2030
New Staff Resources
|  | ▪Planning Mgr (Fall 24) |  | ▪Design Section Mgr | ▪Constr. Mgr
|  | ▪Project Director |  | ▪Program Section Mgr | ▪O&M Mgr (25%)
|  | ▪Support Engineer |  | ▪Govt Relations / Comms
▪Project Controls
▪Admin & Support
Consulting and Construction Resources
Program and Engineering Support Services (owner's rep)
Operations & Flow Allocation
Facilities Plan
Franchise & ROW
Central Pipeline Design Services
Central Pipeline Construction Contract
Central and North Construction Management Services
North Pipeline Design Services
North Pipeline Construction Contract
Products & Outcomes
|  | Project Funding Plan | Project Baseline | Basis of Design
|  | Project Execution Plan | Project Requirements |  | 2029 Decision-point on Wheeling
|  | Procurement Managment Plan | Risk Managment Plan
|  | Stakeholder Management Plan | System Operational Plan
Contract SEPA
|  | TSP SEPA |  |  | Central SEPA
Note on C47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: this includes real property procurement, consultants and contractors.
Note on D46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This includes system wide requirements

## Decade Level
Water Supply Project: Decade-Level Work Plan
| 2025-2029 | 2030-2039 | 2040-2049 | 2050-2059 | 2060-2069 | 2070-2079 | 2080-2089 | 2090-2099
|  |  | Begin using Tacoma Water |  | Begin using Lake Tapps
Projects
OVERALL PROJECT | ☑Planning ▪Franchise & ROW | ☑Planning ▪Franchise & ROW | ☑Decadal Planning | ☑Decadal Planning | ☑Decadal Planning | ☑Decadal Planning | ☑Decadal Planning | ☑Decadal Planning
Central Segment | 2025-2029: ☑Planning ☑Design; 2030-2039: ☑Construction
North Segment | 2025-2029: ☑Planning ▪Design; 2030-2039: ☑Design ☑Construction
Parallel BIP | 2025-2029: ☑Planning; 2040-2049: ☑Design ☑Construction
Booster Pump Station | 2025-2029: ☑Planning; 2040-2049: ☑Design ☑Construction
Storage / Facilities | 2025-2029: ☑Planning; 2040-2049: ☑Design ☑Construction
Eastside Connections | 2025-2029: ☑Planning; 2040-2049: ☑Design ☑Construction
BKR Bellevue | 2025-2029: ☑Planning; 2040-2049: ☑Design ☑Construction
BKR Kirkland/Redmond | 2025-2029: ☑Planning; 2040-2049: ☑ Design; 2050-2059: ☑Construction
BKR Kirkland/Redmond North | 2025-2029: ☑Planning; 2040-2049: ☑ Design; 2050-2059: ☑Construction
Wheeling | 2025-2029: ☑Planning ☑Legislation
South Segment | 2050-2059: ☑ Design; 2060-2069: ☑Construction
Lake Tapps Phase 1 | 2050-2059: ☑ Design; 2060-2069: ☑Construction
Lake Tapps Phase 2 | 2080-2089: ☑Design ☑Construction

## Staffing Phase-in (hidden)
TCP Staffing Plan (2024 $)
Positions | Direct $ | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Planning Mgr | 200000 | bar: 2025 to 2030
Project Director | 250000 | bar: 2025 to 2030
Support Engineer | 175000 | 0.5 | 1 | 1 | 1 | 1 | 1
Design Section Mgr | 200000 | bar: 2027 to 2030
Program Section Mgr | 200000 |  |  | 0.5 | 1 | 1 | 1
Govt Relations / Comms | 175000 |  |  | 0.5 | 1 | 1 | 1
Project Controls | 200000 |  |  | 0.5 | 1 | 1 | 1
Admin & Support | 150000 |  |  | 0.5 | 0.5 | 0.5 | 0.5
Construction Mgr | 200000 | 2029: 0.5; 2030: 1
O&M Mgr | 200000 | 2029: 0.25; 2030: 0.25
Cumulative New FTE |  | 2.5 | 3 | 6 | 7.5 | 8.25 | 8.75
Average Direct Cost |  | 215000 | 208333.3333 | 197916.6667 | 196666.6667 | 196969.697 | 197142.8571
Direct Cost |  | 537500 | 625000 | 1187500 | 1475000 | 1625000 | 1725000
Fully Loaded (1.24x) |  | 666500 | 775000 | 1472500 | 1829000 | 2015000 | 2139000

## Hard Cost (hidden)
Tacoma Cascade Pipeline Budget Sheet
Level 1 Work Package | Schedule | 2022 Estimate | 2024 Estimate (+10%) | 2024 Adjusted (70%) | 2024 Hard Cost@65% | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | Total
Central - 66" | Online by 2035 | 328593750 | 361453125 | 253017187.5 | 164461171.875 | 2030: 24669175.7812; 2031: 32892234.375; 2032: 37003763.6719; 2033: 37003763.6719; 2034: 32892234.375 | 164461171.875
North - 66" | Online by 2038 | 272146250 | 299360875 | 209552612.5 | 136209198.125 | 2034: 17026149.7656; 2035: 34052299.5312; 2036: 34052299.5312; 2037: 34052299.5312; 2038: 17026149.7656 | 136209198.125
Parallel BIP | Online by 2048 | 63765000 | 70141500 | 49099050 | 31914382.5 | 2044: 10638127.5; 2045: 10638127.5; 2046: 10638127.5 | 31914382.5
Booster Pump Station | Online by 2045 | 67083750 | 73792125 | 51654487.5 | 33575416.875 | 2042: 11191805.625; 2043: 11191805.625; 2044: 11191805.625 | 33575416.875
Storage/Facilities | Online by 2048 | 66677500 | 73345250 | 51341675 | 33372088.75 | 2045: 11124029.5833; 2046: 11124029.5833; 2047: 11124029.5833 | 33372088.75
0
Eastside Connections | Online by 2048 | 65322500 | 71854750 | 50298325 | 32693911.25 | 2045: 10897970.4167; 2046: 10897970.4167; 2047: 10897970.4167 | 32693911.25
BKR Bellevue | Online by 2051 | 74598750 | 82058625 | 57441037.5 | 37336674.375 | 2048: 12445558.125; 2049: 12445558.125; 2050: 12445558.125 | 37336674.375
BKR Kirkland/Redmond | Online by 2054 | 123552500 | 135907750 | 95135425 | 61838026.25 | 2051: 20612675.4167; 2052: 20612675.4167; 2053: 20612675.4167 | 61838026.25
BKR Kirkland/Redmond 2 | Online by 2057 | 87920000 | 96712000 | 67698400 | 44003960 | 2054: 14667986.6667; 2055: 14667986.6667; 2056: 14667986.6667 | 44003960
Total Hard Cost w/o Reserves |  |  |  |  | 575404830 | 0 | 0 | 0 | 0 | 0 | 24669175.7812 | 32892234.375 | 37003763.6719 | 37003763.6719 | 49918384.1406 | 34052299.5312 | 34052299.5312 | 34052299.5312 | 17026149.7656 | 0 | 0 | 0 | 11191805.625 | 11191805.625 | 21829933.125 | 32660127.5 | 32660127.5 | 22022000 | 12445558.125 | 12445558.125 | 12445558.125 | 20612675.4167 | 20612675.4167 | 20612675.4167 | 14667986.6667 | 14667986.6667 | 14667986.6667 | 0 | 575404830
Total Hard Cost Reserves | [5 empty] | 0 | 0 | 0 | 0 | 0 | 6167293.9453 | 8223058.5938 | 9250940.918 | 9250940.918 | 12479596.0352 | 8513074.8828 | 8513074.8828 | 8513074.8828 | 4256537.4414 | 0 | 0 | 0 | 2797951.4062 | 2797951.4062 | 5457483.2812 | 8165031.875 | 8165031.875 | 5505500 | 3111389.5312 | 3111389.5312 | 3111389.5312 | 5153168.8542 | 5153168.8542 | 5153168.8542 | 3666996.6667 | 3666996.6667 | 3666996.6667 | 0 | 86220978.5938
Total Construction Budget | [10 empty] | 30836469.7266 | 41115292.9688 | 46254704.5898 | 46254704.5898 | 62397980.1758 | 42565374.4141 | 42565374.4141 | 42565374.4141 | 21282687.207 | 0 | 0 | 0 | 13989757.0312 | 13989757.0312 | 27287416.4062 | 40825159.375 | 40825159.375 | 27527500 | 15556947.6562 | 15556947.6562 | 15556947.6562 | 25765844.2708 | 25765844.2708 | 25765844.2708 | 18334983.3333 | 18334983.3333 | 18334983.3333 | 0 | 661625808.5938
|  | Source: | CWA - Cost Estimate TM Tables_FINAL w Scenarios 021423.xlsx
Note on A9: Andy Baker: Get more definition on this scope of work
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Without Contingency / Sales Tax: $197,923,750
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Was 50000000

## Soft Cost (hidden)
Tacoma Cascade Pipeline Budget Sheet
Level 1 Work Package | Schedule | 2022 Dollars | 2024 Dollars | 2024 Adjusted | Consultant FTE | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | Total
TCP Program Management |  | 0 | 0 | 0 | 44.4679 | 1.5 | 1.75 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 44.25
Central | Online by 2035 | 328593750 | 361453125 | 253017187.5 | 70.8448 | 2025: 1.5; 2026: 1.5; 2027: 10; 2028: 15; 2029: 15; 2030: 5; 2031: 4; 2032: 4; 2033: 4; 2034: 4; 2035: 4; 2036: 2; 2037: 0.5; 2038: 0.5 | 71
North | Online by 2038 | 197923750 | 217716125 | 152401287.5 | 42.6724 | 2025: 0.5; 2026: 0.5; 2029: 2.5; 2030: 5; 2031: 6; 2032: 6; 2033: 7; 2034: 3; 2035: 3; 2036: 3; 2037: 3; 2038: 2; 2039: 1 | 42.5
Parallel BIP | Online by 2048 | 63765000 | 70141500 | 49099050 | 12.7658 | 2025: 0.1; 2026: 0.1; 2040: 0.5; 2041: 1; 2042: 3; 2043: 3; 2044: 3; 2045: 1.3; 2046: 1.25; 2047: 1.25; 2048: 0.5 | 15
Booster Pump Station | Online by 2045 | 67083750 | 73792125 | 51654487.5 | 13.4302 | 2025: 0.1; 2026: 0.1; 2039: 2; 2040: 3; 2041: 3; 2042: 1.25; 2043: 1.25; 2044: 1; 2045: 0.5 | 12.2
Storage/Facilities | Online by 2048 | 50000000 | 55000000 | 38500000 | 10.01 | 2025: 0.1; 2026: 0.1; 2042: 2.3; 2043: 3; 2044: 3; 2045: 1; 2046: 1; 2047: 1; 2048: 0.5 | 12
0
Eastside Connections | Online by 2048 | 65322500 | 71854750 | 50298325 | 15.0895 | 2025: 0.1; 2026: 0.1; 2042: 1; 2043: 3; 2044: 4; 2045: 3.8; 2046: 1; 2047: 1; 2048: 1 | 15
BKR Bellevue | Online by 2051 | 74598750 | 82058625 | 57441037.5 | 17.2323 | 2025: 0.1; 2026: 0.1; 2044: 3; 2045: 3; 2046: 4; 2047: 3; 2048: 1; 2049: 1; 2050: 1; 2051: 0.8 | 17
BKR Kirkland/Redmond | Online by 2054 | 123552500 | 135907750 | 95135425 | 28.5406 | 2025: 0.1; 2026: 0.1; 2048: 5; 2049: 5.3; 2050: 5.5; 2051: 5.5; 2052: 1.5; 2053: 1.5; 2054: 1.5; 2055: 1 | 27
BKR Kirkland/Redmond 2 | Online by 2057 | 87920000 | 96712000 | 67698400 | 20.3095 | 2025: 0.1; 2026: 0.1; 2050: 2; 2051: 4; 2052: 4.3; 2053: 4; 2054: 1.5; 2055: 1.5; 2056: 1.5; 2057: 1 | 20
Total |  | 1058760000 | 1164636000 | 815245200 | 275.363 | 4.2 | 4.45 | 12 | 17 | 19.5 | 12 | 12 | 12 | 13 | 9 | 9 | 7 | 5.5 | 4 | 4.5 | 4.5 | 5 | 8.55 | 11.25 | 15 | 10.6 | 8.25 | 7.25 | 9 | 7.3 | 9.5 | 11.3 | 6.8 | 6.5 | 4 | 3 | 2 | 1 | 275.95
Cascade FTE | [5 empty] | 2 | 3 | 6 | 8 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 8 | 8 | 8 | 7 | 7 | 3 | 3 | 3 | 2 | 253
Project Reserves
Level 1 Work Package |  | 2022 Dollars | 2024 Dollars | 2024 Adjusted | Consultant FTE | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | Grand Total
TCP Program Management |  | 0 | 0 | 0 | 44.4679 | 750000 | 875000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 750000 | 750000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 250000 | 250000 | 0 | 22125000
Central | Online by 2035 | 328593750 | 361453125 | 253017187.5 | 65.7845 | 750000 | 750000 | 5000000 | 7500000 | 7500000 | 2500000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 1000000 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35500000
North | Online by 2038 | 197923750 | 217716125 | 152401287.5 | 42.6724 | 250000 | 250000 | 0 | 0 | 1250000 | 2500000 | 3000000 | 3000000 | 3500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1000000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21250000
Parallel BIP | Online by 2048 | 63765000 | 70141500 | 49099050 | 14.7297 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 500000 | 1500000 | 1500000 | 1500000 | 650000 | 625000 | 625000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500000
Booster Pump Station | Online by 2045 | 67083750 | 73792125 | 51654487.5 | 12.3971 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1500000 | 1500000 | 625000 | 625000 | 500000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6100000
Storage/Facilities | Online by 2048 | 50000000 | 55000000 | 38500000 | 11.55 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000 | 1500000 | 1500000 | 500000 | 1500000 | 500000 | 500000 | 500000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000000
Eastside Connections | Online by 2048 | 65322500 | 71854750 | 50298325 | 15.0895 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1500000 | 2000000 | 1900000 | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500000
BKR Bellevue | Online by 2051 | 74598750 | 82058625 | 57441037.5 | 17.2323 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 2000000 | 1500000 | 500000 | 500000 | 500000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 8500000
BKR Kirkland/Redmond | Online by 2054 | 123552500 | 135907750 | 95135425 | 26.6379 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2650000 | 2750000 | 2750000 | 750000 | 750000 | 750000 | 500000 | 0 | 0 | 13500000
BKR Kirkland/Redmond 2 | Online by 2057 | 87920000 | 96712000 | 67698400 | 20.3095 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 2000000 | 2150000 | 2000000 | 750000 | 750000 | 750000 | 500000 | 9500000
Total |  | 1058760000 | 1164636000 | 815245200 | 270.8708 | 2100000 | 2225000 | 6000000 | 8500000 | 9750000 | 6000000 | 6000000 | 6000000 | 6500000 | 4500000 | 4500000 | 3500000 | 2750000 | 2000000 | 2250000 | 3400000 | 4000000 | 4625000 | 4625000 | 7500000 | 5300000 | 4125000 | 3625000 | 4500000 | 3650000 | 4750000 | 5650000 | 3400000 | 3250000 | 2000000 | 1500000 | 1000000 | 500000 | 139475000
Total Cascade FTE | [5 empty] | 666500 | 775000 | 1472500 | 1829000 | 2015000 | 2139000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 1956000 | 1956000 | 1956000 | 1711000 | 1711000 | 733000 | 733000 | 733000 | 489000 | 61084000
Total Soft Cost w/o reserves | [5 empty] | 2766500 | 3000000 | 7472500 | 10329000 | 11765000 | 8139000 | 8261000 | 8261000 | 8761000 | 6761000 | 6761000 | 5761000 | 5011000 | 4261000 | 4511000 | 5661000 | 6261000 | 6886000 | 6886000 | 9761000 | 7561000 | 6386000 | 5886000 | 6761000 | 5606000 | 6706000 | 7606000 | 5111000 | 4961000 | 2733000 | 2233000 | 1733000 | 989000 | 200559000
Total Soft Cost Reserves | [5 empty] | 276650 | 300000 | 747250 | 1032900 | 1176500 | 813900 | 826100 | 826100 | 876100 | 676100 | 676100 | 576100 | 501100 | 426100 | 451100 | 566100 | 626100 | 688600 | 688600 | 976100 | 756100 | 638600 | 588600 | 676100 | 560600 | 670600 | 760600 | 511100 | 496100 | 273300 | 223300 | 173300 | 98900 | 20055900
Total Soft Cost Budget | [5 empty] | 3043150 | 3300000 | 8219750 | 11361900 | 12941500 | 8952900 | 9087100 | 9087100 | 9637100 | 7437100 | 7437100 | 6337100 | 5512100 | 4687100 | 4962100 | 6227100 | 6887100 | 7574600 | 7574600 | 10737100 | 8317100 | 7024600 | 6474600 | 7437100 | 6166600 | 7376600 | 8366600 | 5622100 | 5457100 | 3006300 | 2456300 | 1906300 | 1087900 | 220614900
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume 30% Overall Contingency
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume $500k per FTE and 15% total consultant fee
Note on G38: Andy Baker: Add to Operating Contingency
Note on H38: Andy Baker: 50/50 Operating/Capital Contingency
Note on I38: Andy Baker: Capital Contingency
Note on J24: Andy Baker: Consider bringing forward if rates can accommodate.

## Total Cash Flow (hidden)
Year | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | Grand Total
Soft Cost w/o reserves | 2766500 | 3000000 | 7472500 | 10329000 | 11765000 | 8139000 | 8261000 | 8261000 | 8761000 | 6761000 | 6761000 | 5761000 | 5011000 | 4261000 | 4511000 | 5661000 | 6261000 | 6886000 | 6886000 | 9761000 | 7561000 | 6386000 | 5886000 | 6761000 | 5606000 | 6706000 | 7606000 | 5111000 | 4961000 | 2733000 | 2233000 | 1733000 | 989000 | 201548000
Soft Cost Reserves | 276650 | 300000 | 747250 | 1032900 | 1176500 | 813900 | 826100 | 826100 | 876100 | 676100 | 676100 | 576100 | 501100 | 426100 | 451100 | 566100 | 626100 | 688600 | 688600 | 976100 | 756100 | 638600 | 588600 | 676100 | 560600 | 670600 | 760600 | 511100 | 496100 | 273300 | 223300 | 173300 | 98900 | 20154800
Subtotal Soft Cost Budgtet | 3043150 | 3300000 | 8219750 | 11361900 | 12941500 | 8952900 | 9087100 | 9087100 | 9637100 | 7437100 | 7437100 | 6337100 | 5512100 | 4687100 | 4962100 | 6227100 | 6887100 | 7574600 | 7574600 | 10737100 | 8317100 | 7024600 | 6474600 | 7437100 | 6166600 | 7376600 | 8366600 | 5622100 | 5457100 | 3006300 | 2456300 | 1906300 | 1087900 | 221702800
Hard Cost w/o Reserves | 0 | 0 | 0 | 0 | 0 | 24669175.7812 | 32892234.375 | 37003763.6719 | 37003763.6719 | 49918384.1406 | 34052299.5312 | 34052299.5312 | 34052299.5312 | 17026149.7656 | 0 | 0 | 0 | 11191805.625 | 11191805.625 | 21829933.125 | 32660127.5 | 32660127.5 | 22022000 | 12445558.125 | 12445558.125 | 12445558.125 | 20612675.4167 | 20612675.4167 | 20612675.4167 | 14667986.6667 | 14667986.6667 | 14667986.6667 | 0 | 575404830
Hard Cost Reserves | 0 | 0 | 0 | 0 | 0 | 6167293.9453 | 8223058.5938 | 9250940.918 | 9250940.918 | 12479596.0352 | 8513074.8828 | 8513074.8828 | 8513074.8828 | 4256537.4414 | 0 | 0 | 0 | 2797951.4062 | 2797951.4062 | 5457483.2812 | 8165031.875 | 8165031.875 | 5505500 | 3111389.5312 | 3111389.5312 | 3111389.5312 | 5153168.8542 | 5153168.8542 | 5153168.8542 | 3666996.6667 | 3666996.6667 | 3666996.6667 | 0 | 143851207.5
Subtotal Construction Budget | 0 | 0 | 0 | 0 | 0 | 30836469.7266 | 41115292.9688 | 46254704.5898 | 46254704.5898 | 56593548.7305 | 30956511.5234 | 30956511.5234 | 30956511.5234 | 15478255.7617 | 0 | 0 | 0 | 13989757.0312 | 13989757.0312 | 27287416.4062 | 37347205.7292 | 37347205.7292 | 24049546.3542 | 15556947.6562 | 15556947.6562 | 15556947.6562 | 25765844.2708 | 25765844.2708 | 25765844.2708 | 18334983.3333 | 18334983.3333 | 18334983.3333 | 0 | 719256037.5
Total Budget w/o Risk Reserves | 3043150 | 3300000 | 8219750 | 11361900 | 12941500 | 39789369.7266 | 50202392.9688 | 55341804.5898 | 55891804.5898 | 64030648.7305 | 38393611.5234 | 37293611.5234 | 36468611.5234 | 20165355.7617 | 4962100 | 6227100 | 6887100 | 21564357.0312 | 21564357.0312 | 38024516.4062 | 45664305.7292 | 44371805.7292 | 30524146.3542 | 22994047.6562 | 21723547.6562 | 22933547.6562 | 34132444.2708 | 31387944.2708 | 31222944.2708 | 21341283.3333 | 20791283.3333 | 20241283.3333 | 1087900 | 940958837.5
Risk Reserves (30%) | 912945 | 990000 | 2465925 | 3408570 | 3882450 | 11936810.918 | 15060717.8906 | 16602541.377 | 16767541.377 | 19209194.6191 | 11518083.457 | 11188083.457 | 10940583.457 | 6049606.7285 | 1488630 | 1868130 | 2066130 | 6469307.1094 | 6469307.1094 | 11407354.9219 | 13699291.7188 | 13311541.7188 | 9157243.9062 | 6898214.2969 | 6517064.2969 | 6880064.2969 | 10239733.2812 | 9416383.2812 | 9366883.2812 | 6402385 | 6237385 | 6072385 | 326370 | 265226857.5
Total Budget | 3956095 | 4290000 | 10685675 | 14770470 | 16823950 | 51726180.6445 | 65263110.8594 | 71944345.9668 | 72659345.9668 | 83239843.3496 | 49911694.9805 | 48481694.9805 | 47409194.9805 | 26214962.4902 | 6450730 | 8095230 | 8953230 | 28033664.1406 | 28033664.1406 | 49431871.3281 | 59363597.4479 | 57683347.4479 | 39681390.2604 | 29892261.9531 | 28240611.9531 | 29813611.9531 | 44372177.5521 | 40804327.5521 | 40589827.5521 | 27743668.3333 | 27028668.3333 | 26313668.3333 | 1414270 | 1206185695
Export for Rate Model | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | Grand Total
Operating
Professional Services
TCP Program Management | 750000 | 437500 | [31 empty] | 1187500
Central | 750000 | 375000 | [31 empty] | 1125000
North | 250000 | 125000 | [31 empty] | 375000
Parallel BIP | 50000 | 25000 | [31 empty] | 75000
Booster Pump Station | 50000 | 25000 | [31 empty] | 75000
Storage/Facilities | 50000 | 25000 | [31 empty] | 75000
Eastside Connections | 50000 | 25000 | [31 empty] | 75000
BKR Bellevue | 50000 | 25000 | [31 empty] | 75000
BKR Kirkland/Redmond | 50000 | 25000 | [31 empty] | 75000
BKR Kirkland/Redmond 2 | 50000 | 25000 | [31 empty] | 75000
Subtotal - Professional Svcs | 2100000 | 1112500 | [31 empty] | 3212500
Salaries | 666500 | 387500 | [31 empty] | 1054000
TCP Operating Contingency | 276650 | 150000 | [31 empty] | 426650
Total | 3043150 | 1650000 | [31 empty] | 4693150
Capital (Soft & Hard Costs)
TCP Program Management |  | 437500 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 750000 | 750000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 250000 | 250000 | 0 | 20937500
Central |  | 375000 | 5000000 | 7500000 | 7500000 | 27169175.7812 | 34892234.375 | 39003763.6719 | 39003763.6719 | 34892234.375 | 2000000 | 1000000 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198836171.875
North |  | 125000 | 0 | 0 | 1250000 | 2500000 | 3000000 | 3000000 | 3500000 | 18526149.7656 | 35552299.5312 | 35552299.5312 | 35552299.5312 | 18026149.7656 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157084198.125
Parallel BIP |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 500000 | 1500000 | 1500000 | 12138127.5 | 11288127.5 | 11263127.5 | 625000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39339382.5
Booster Pump Station |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1500000 | 1500000 | 11816805.625 | 11816805.625 | 11691805.625 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39600416.875
Storage/Facilities |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000 | 1500000 | 1500000 | 500000 | 1500000 | 11624029.5833 | 11624029.5833 | 11624029.5833 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41297088.75
Eastside Connections |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1500000 | 2000000 | 12797970.4167 | 11397970.4167 | 11397970.4167 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40118911.25
BKR Bellevue |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 2000000 | 1500000 | 12945558.125 | 12945558.125 | 12945558.125 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 45761674.375
BKR Kirkland/Redmond |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2650000 | 2750000 | 23362675.4167 | 21362675.4167 | 21362675.4167 | 750000 | 500000 | 0 | 0 | 75263026.25
BKR Kirkland/Redmond 2 |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 2000000 | 2150000 | 2000000 | 15417986.6667 | 15417986.6667 | 15417986.6667 | 500000 | 53928960
Subtotal - Work Packages |  | 1112500 | 6000000 | 8500000 | 9750000 | 30669175.7812 | 38892234.375 | 43003763.6719 | 43503763.6719 | 54418384.1406 | 38552299.5312 | 37552299.5312 | 36802299.5312 | 19026149.7656 | 2250000 | 3400000 | 4000000 | 15816805.625 | 15816805.625 | 29329933.125 | 37960127.5 | 36785127.5 | 25647000 | 16945558.125 | 16095558.125 | 17195558.125 | 26262675.4167 | 24012675.4167 | 23862675.4167 | 16667986.6667 | 16167986.6667 | 15667986.6667 | 500000 | 712167330
0
Salaries |  | 387500 | 1472500 | 1829000 | 2015000 | 2139000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 2261000 | 1956000 | 1956000 | 1956000 | 1711000 | 1711000 | 733000 | 733000 | 733000 | 489000 | 60519000
Addition to Capital Contingency |  | 150000 | 747250 | 1032900 | 1176500 | 6981193.9453 | 9049158.5938 | 10077040.918 | 10127040.918 | 13155696.0352 | 9189174.8828 | 9089174.8828 | 9014174.8828 | 4682637.4414 | 451100 | 566100 | 626100 | 3486551.4062 | 3486551.4062 | 6433583.2812 | 8921131.875 | 8803631.875 | 6094100 | 3787489.5312 | 3671989.5312 | 3781989.5312 | 5913768.8542 | 5664268.8542 | 5649268.8542 | 3940296.6667 | 3890296.6667 | 3840296.6667 | 98900 | 163579357.5
Total |  | 1650000 | 8219750 | 11361900 | 12941500 | 39789369.7266 | 50202392.9688 | 55341804.5898 | 55891804.5898 | 69835080.1758 | 50002474.4141 | 48902474.4141 | 48077474.4141 | 25969787.207 | 4962100 | 6227100 | 6887100 | 21564357.0312 | 21564357.0312 | 38024516.4062 | 49142259.375 | 47849759.375 | 34002100 | 22994047.6562 | 21723547.6562 | 22933547.6562 | 34132444.2708 | 31387944.2708 | 31222944.2708 | 21341283.3333 | 20791283.3333 | 20241283.3333 | 1087900 | 936265687.5
Operating + Capital | 3043150 | 3300000 | 8219750 | 11361900 | 12941500 | 39789369.7266 | 50202392.9688 | 55341804.5898 | 55891804.5898 | 69835080.1758 | 50002474.4141 | 48902474.4141 | 48077474.4141 | 25969787.207 | 4962100 | 6227100 | 6887100 | 21564357.0312 | 21564357.0312 | 38024516.4062 | 49142259.375 | 47849759.375 | 34002100 | 22994047.6562 | 21723547.6562 | 22933547.6562 | 34132444.2708 | 31387944.2708 | 31222944.2708 | 21341283.3333 | 20791283.3333 | 20241283.3333 | 1087900 | 940958837.5
Budget w/o Risk Reserve | 3043150 | 3300000 | 8219750 | 11361900 | 12941500 | 39789369.7266 | 50202392.9688 | 55341804.5898 | 55891804.5898 | 64030648.7305 | 38393611.5234 | 37293611.5234 | 36468611.5234 | 20165355.7617 | 4962100 | 6227100 | 6887100 | 21564357.0312 | 21564357.0312 | 38024516.4062 | 45664305.7292 | 44371805.7292 | 30524146.3542 | 22994047.6562 | 21723547.6562 | 22933547.6562 | 34132444.2708 | 31387944.2708 | 31222944.2708 | 21341283.3333 | 20791283.3333 | 20241283.3333 | 1087900 | 884089525
Addition to Capital Contingency (Risk) |  |  | 2465925 | 3408570 | 3882450 | 11936810.918 | 15060717.8906 | 16602541.377 | 16767541.377 | 19209194.6191 | 11518083.457 | 11188083.457 | 10940583.457 | 6049606.7285 | 1488630 | 1868130 | 2066130 | 6469307.1094 | 6469307.1094 | 11407354.9219 | 13699291.7188 | 13311541.7188 | 9157243.9062 | 6898214.2969 | 6517064.2969 | 6880064.2969 | 10239733.2812 | 9416383.2812 | 9366883.2812 | 6402385 | 6237385 | 6072385 | 326370 | 263323912.5
Total Budget | 3043150 | 3300000 | 10685675 | 14770470 | 16823950 | 51726180.6445 | 65263110.8594 | 71944345.9668 | 72659345.9668 | 89044274.7949 | 61520557.8711 | 60090557.8711 | 59018057.8711 | 32019393.9355 | 6450730 | 8095230 | 8953230 | 28033664.1406 | 28033664.1406 | 49431871.3281 | 62841551.0938 | 61161301.0938 | 43159343.9062 | 29892261.9531 | 28240611.9531 | 29813611.9531 | 44372177.5521 | 40804327.5521 | 40589827.5521 | 27743668.3333 | 27028668.3333 | 26313668.3333 | 1414270 | 1204282750
| 912945 | 990000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5804431.4453 | -11608862.8906 | -11608862.8906 | -11608862.8906 | -5804431.4453 | 0 | 0 | 0 | 0 | 0 | 0 | -3477953.6458 | -3477953.6458 | -3477953.6458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost reserves for hard and soft cost, aka contingency reserves are for cost reserved for known unknowns such as variances on linear foot of pipe or project elements that are less defined at the time of baseine project cost and schedule
Risk Reserves aka Management Reserves are reserves for cost incured outside of project team control including external imposed conditions not known to the project team at the time of baseline project cost and schedule.

## Export for Budget (inflated) (hidden)
TCP Budget (Escalated to Year-of-Expenditure $)
| 2025 | 2026 | 2027 | 2028 | 2029 | 2030
CPI | 3% | 3% | 3% | 3% | 3% | 3%
Cumulative Inflation Multiplier | 103% | 106.1% | 109.3% | 112.6% | 115.9% | 119.4%
Construction Cost Inflation | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5%
Construction Cost Inflation Multiplier | 103.5% | 107.1% | 110.9% | 114.8% | 118.8% | 122.9%
Operating
Professional Services
TCP Program Management | 776000 | 469000
Central | 776000 | 402000
North | 259000 | 134000
Parallel BIP | 52000 | 27000
Booster Pump Station | 52000 | 27000
Storage/Facilities | 52000 | 27000
Eastside Connections | 52000 | 27000
BKR Bellevue | 52000 | 27000
BKR Kirkland/Redmond | 52000 | 27000
BKR Kirkland/Redmond 2 | 52000 | 27000
Subtotal - Professional Svcs | 2175000 | 1194000
Salaries | 690000 | 415000
TCP Operating Contingency | 286000 | 161000
Total Operating | 3151000 | 1770000
Capital (Soft & Hard Costs)
TCP Program Management |  | 469000 | 1109000 | 1148000 | 1188000 | 1229000
Central |  | 402000 | 5544000 | 8606000 | 8908000 | 33398000
North |  | 134000 | 0 | 0 | 1485000 | 3073000
Parallel BIP |  | 27000 | 0 | 0 | 0 | 0
Booster Pump Station |  | 27000 | 0 | 0 | 0 | 0
Storage/Facilities |  | 27000 | 0 | 0 | 0 | 0
Eastside Connections |  | 27000 | 0 | 0 | 0 | 0
BKR Bellevue |  | 27000 | 0 | 0 | 0 | 0
BKR Kirkland/Redmond |  | 27000 | 0 | 0 | 0 | 0
BKR Kirkland/Redmond 2 |  | 27000 | 0 | 0 | 0 | 0
Subtotal - Work Packages |  | 1194000 | 6653000 | 9754000 | 11581000 | 37700000
Salaries |  | 415000 | 1633000 | 2099000 | 2393000 | 2629000
TCP Capital Contingency |  | 161000 | 828000 | 1185000 | 1397000 | 8582000
TCP Risk Reserve |  | 0 | 2734000 | 3911000 | 4611000 | 14673000
Total Capital |  | 1770000 | 11848000 | 16949000 | 19982000 | 63584000
Project Total (Operating & Capital) | 3151000 | 3540000 | 11848000 | 16949000 | 19982000 | 63584000
Check

## Capital Scenario Comparison (hidden)
Total Tacoma Connection Capital Costs (2024$)
Initial System Planning, Capital Portion | 1262500
Hard Costs
Central (2030-2034) | 164461171.875
North (2034-2038) | 136209198.125
Hard Cost Contingency (25%) | 75167592.5
Soft Costs
TCP Program Management, 2027-2039 | 12500000
Central (2027-2038) | 34000000
North (2029-2039) | 20750000
Staffing (2027-2039) | 27804500
Soft Cost Contingency (10%) | 9505450
Project Reserve (30%) | 144498123.75
Total | 626158536.25
Total Lake Tapps Treatment Costs (2022$)
LTP - North Segment | 295195000
LTP - Central Segment | 407640000
LTP - South Segment | 323765000
Storage Reservoir | 66677500
Booster Pump Station | 67083750
Lake Tapps Treatment Plant (Phase 1) w. Ozone | 336777568
Subtotal | 1497138818
Escalated to 2024$ by 10% (consistent with Henry's estimate above) | 1646852699.8
Payments to Seattle for Supply
Base Scenario
Cascade Block Payments | 405990208
Additional Block Payments | 146540015
Total | 552530223
TPU Smoothed Scenario
Cascade Block Payments (2025-2041) | 405990208
Additional Block Payments | 146540015
Transition Payments (2026-2033) | 0
Total | 552530223
SPU Smoothed Scenario
Cascade Block Payments (2025-2041) | 264258671
Additional Block Payments | 354441112
Transition Payments (2026-2033) | 20000000
Total | 638699783
Difference | 86169560

## Quarter Level (hidden)
Transmission Project Workplan
| Major |  |  | (days) | (months) | Dependencies |  | Schedule |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055
# | Task | Subtask |  | Duration | Duration | Start | Stop | Start | Stop | Resources | Notes | Q1 2024 | Q2 2024 | Q3 2024 | Q4 2024 | Q1 2025 | Q2 2025 | Q3 2025 | Q4 2025 | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | Q1 2027 | Q2 2027 | Q3 2027 | Q4 2027 | Q1 2028 | Q2 2028 | Q3 2028 | Q4 2028 | Q1 2029 | Q2 2029 | Q3 2029 | Q4 2029
1 | Project Planning
1.1 |  | Member Distribution System Requirements | [5 empty] | 2024-07-01 | 2025-01-01 |  | Do we know enough today, or is there more information we need in order to do the Optimization analysis? Working assumption: current volumes & demands? To what extent do we need member buy-off or consultation on the assumptions we use in our TSP?
1.1.1 |  |  | Policy regarding delivery points | [7 empty] | Already exists - review if needs any updates
1.2 |  | Transmission Project Requirements | [5 empty] | 2024-04-01 | 2026-01-01 | Planning Manager
1.2.1 |  |  | Total Volumes |  |  |  |  | 2024-04-01 | 2026-01-01 | Planning Manager + Economists
1.2.2 |  |  | Peak Demands |  |  |  |  | 2024-04-01 | 2025-06-01 | Planning Manager + Economists
1.2.3 |  |  | Economic argument for peak conservation |  |  |  |  | 2024-04-01 | 2025-06-01 | Planning Manager + Economists
1.2.4 |  |  | Rate structure related to peaking |  |  |  |  | 2025-01-01 | 2026-01-01 | Planning Manager + Economists
1.2.5 |  |  | Policy regarding independent supply for peak |  |  |  |  | 2025-01-01 | 2026-01-01 | Planning Manager + Economists
1.3 |  | Alignment & Siting |  |  |  |  | FA 1.2End | 2025-09-01 | 2027-04-01 | Planning Manager + Consultants | How much of 1.2 is necessary to complete before start?
1.3.1 |  |  | Optimization - How many pipes?
1.3.2 |  |  | Optimization - Other?
1.3.3 |  |  | Terminal storage?
1.3.4 |  |  | Parallel BIP
1.4 |  | Transmission & Supply Plan | [5 empty] | 2025-01-01 | 2026-12-31
|  |  | Get the Planning Manager hired | [7 empty] | What's the earliest we could start?
|  |  | RFQ Development | [7 empty] | How much can we start before
|  |  | TSP Development |  | 24 | [5 empty] | This includes pre-design for Central & North segments
Alternative: miniTSP update if forced to by the BIP
2 | Wheeling
2.1 |  | Voluntary Decision by SPU / Mayor |  | 275 | 9 | None |  | 2024-04-01 | 2025-01-01
2.2 |  | Legislative Strategy |  | 942 | 31 | None |  | 2024-09-01 | 2027-04-01 | Lobbyist, Consultant Team, Economist, Legal | Assume it takes 2 full cycles to pass. Resiliency (climate, earthquakes, etc.) is the core strategy, economic efficiency and benefit secondary
2.3 |  | Technical Evaluation |  | 365 |  | None |  | 2025-07-01 | 2026-07-01
2.3.1 |  |  | Location
2.3.2 |  |  | Chemistry
2.3.3 |  |  | Flow
2.3.4 |  |  | Pressure
3 | Real Property
3.1 |  | King County Franchise | [5 empty] | Q4 2024 |  | Consultant / Legal / Planning Mgr
3.2 |  | SPU
3.3 |  | Private | [5 empty] | Q1 2026
4 | SEPA |  |  |  |  | SA 1.3Start | FA 1.3End
5 | Permitting |  |  |  |  | SA 6 Start
6 | Central Segment
Planning
Design
|  | Construction | [5 empty] | 2030-01-01 | 1934-12-31
7 | North Segment
Planning
Design
Construction